## Planning Projet DS
1
|  | S1 | S2 | S3 | S4 | S5 | S6 | S7 |  | S8 | S9 | S10
|  | semaine1 | semaine2 | semaine3 | semaine4 | semaine5 | semaine6 | semaine7 | semaine8 | semaine9 | semaine10
Data Science Project_2024 | Project Coordinator
| Project Phases | S1: Phase 1: Business Understanding, Data Requirements, Data Collection and Understanding; S4: Phase 2: Data Preparation; S7: Phase 3: Data Modeling and Evaluation |  |  | Phase 4: Deployment | Final Validation
| Session Type | Project Launch | Coaching | Skill 1_Validation | Coaching | Coaching | Skill2_Validation | Coaching | Coaching | Skill3_Validation | Coaching